## Slide 1: Coursera Integration Project Kickoff
© 2019 YASH Technologies | www.yash.com | Confidential
Date: Feb 13, 2019

## Slide 2: Agenda
Team Introductions
Project Objectives
Risks Mitigation Strategies & Assumptions
Project Schedule
Deliverables
Project Control and Monitoring
Status Reports

## Slide 3: YASH Team – Roles & Responsibilities
Name | Email | Role | Responsibility | Location/Contact
Ramesh Suryaneni | Ramesh.Suryaneni@yash.com | Solution Architect | Managing the solution engineering in relation to specific business problems. | Offshore
Mitul Deshmukh | mitul.deshmukh@yash.com | Project Manager | Detailed project plan to monitor , track progress , And weekly status report | Offshore
Zia Uddin Shaikh | zia.shaikh@yash.com | Technical Java Lead | Design, build, and maintain efficient, reusable, and reliable Java code | Offshore
Nitish Aggarwal | nitish.aggarwal@yash.com | Java Developer | Write well designed, testable, efficient code | Offshore
Isha Tiwari | isha.tiwari@yash.com | Java Developer | Write well designed, testable, efficient code | Offshore
Sonali Fulsunder | sonali.fulsundar@yash.com | Functional Tester | Write test cases and execute | Offshore
Gulshan Kumar | gulshan.kumar@yash.com | AWS Infra Developer | Setting up AWS infrastructure | Offshore
Devesh Neema | deveshn@yash.com | Delivery Manager | Overall project delivery/execution and Client interaction | Onsite
Nishikant Purohit | Nishikant.purohit@yash.com | Project Oversight | Project liaison between Yash and Coursera teams. Yash SF team Project management. | Onshore
Jawaid Allam | Jawaid.Allam@yash.com | SF LMS Functional Consultant | Configure SF LMS system. Assist in SF related testing | Offshore
Nagesh Venkat Polu | Nagesh.Polu@yash.com | SF LMS Functional Consultant | Configure SF LMS system and Integration Center. Assist in SF related testing | Offshore

## Slide 4: Coursera Team – Key Contacts
Name | Email Address
Himanshu Koshe | hkoshe@coursera.org
Benjamin Littlemore | blittlemore@coursera.org (Project Manager and Technical Contact)

## Slide 5: Project Objectives
S.No | Description | Owner | Priority
1 | Get the response from the Content API, from Coursera, and send/map/post to SSF LMS system. | YASH | H
2 | Get the response from the program API, from Coursera, and send/map/post to SSF LMS system. | YASH | H
3 | Get the response from the Completion/Status API , from Coursera, and send/map/post to SFF LMS system. | YASH | H
4 | Post user invitation to Coursera using the invite API, using the SSF LMS/App specific identifier. | YASH | M
5 | Get/Read user Information(e.g. CSV file ) from SSF LMS system and send/post to Coursera Server. | YASH | M
6 | Application Deployment and Deere integration Setup | YASH/COURSERA | H

## Slide 6: Project Schedule
Go Live Date:
Friday, August 9th 2019
India Holidays:
May 1, 2019 Labor day

## Slide 7: Risks and Assumptions
Coursera and SSF LMS will provide access to the AWS Repo and all API Access.
SSF LMS User information will be available on SFTP server in specific file Format and location.
Coursera will provide the location access where user information will be placed, which is coming form the SSF LMS system.
Risk Level | Risk Description | Mitigation Strategy | Owner
M | Additional features identified during the project execution | Revised Timeline and estimates. | YASH/Coursera
M | Integration requirement other than Coursera | Evaluate impact to project timeline and adjust scope if required. | YASH/Coursera
L | IT Resource availability | Monitor availability based on completion of tasks, escalate early if issues arise. | YASH
H | Delay in receiving access for SSF LMS and Couresra API env | YASH will send request for required access needed in advance. | YASH/Coursera
M | Timely responses for the clarification/sign-off as and when required | Project schedule may get changed if there are dependencies on tasks/activities. | YASH/Coursera
L | Providing Test data before start of development. | Testing schedule may be delayed. | Coursera
Risks:
Assumptions:

## Slide 8: Out Of Scope
Changes to Standard SSF APIs and access required for middleware.
Changes in Coursera Standard APIs and access required for middleware.
SSO between SSF and Coursera.
AWS account management.

## Slide 9: Project Control and Monitoring
Project Escalation Hierarchy
Level | YASH Contact | Coursera Contact
FIRST | Mitul Deshmukh (Mitul.Deshmukh@yash.com) | 
SECOND | Nishikant.Purohit <Nishikant.Purohit@yash.com> | 
THIRD | Hari P Vyakarnam <harip@yash.com> | 
Any Requirement(s) not mentioned in the requirement document will be considered change request
The YASH functional lead reviews the requirement or issue and determines that the resolution will lead to a change in scope, defined as a change that will impact cost, schedule, or staffing.
The proposed change is documented in a scope change order, including the impact on schedule, cost, and staffing.
The scope change order is reviewed by project's scope change board (comprising Coursera and YASH), and approved by signing the change order.
Project Change
Management

## Slide 10: Status Reports
Project Communication
Weekly Status Calls
and Report
Project Plan Review
Communication between Coursera & YASH PM will be by means of Email, Phone, WebEx
Weekly status report will be sent to all stake holders by YASH PM and a review call will be scheduled to discuss the same.
Bi-Weekly Review of the Project Plan by both the PM’s to track the project status and discuss any Issues.

## Slide 11
THANK YOU